## Sheet 1
Table 1
|  | Literature, Research | Setup Working Environment | MS App: Network Communication Intensive Container (Flask & Locust) | MS App: CPU Intensive Container (Prime Calc?) | MS App: Disk R/W Intensive Container (MongoDB) | MS App: Memory Intensive Container (Redis) | Migration: Containers Singularly | (Migration: MS App) | Comparison Results 2 Methods (STS VS CRIU) | (Live Migration) | Finish Paper | (Presentation)
W1
TUE 19.9 | x
x
W2 | x
TUE 26.9 | x
x
W3 | x
TUE 3.10 | x
x
W4 | x
TUE 10.10 | x
x
W5 | x
TUE 17.10 | x
x
W6 | x
TUE 24.10 | x
x
W7 | x
TUE 31.10 | x
| x |  |  |  | M1
W8 | x
TUE 7.11 | x
x
W9 | x
TUE 14.11 | x
x
W10 | x
TUE 21.11 | x
x
W11 | x
TUE 28.11 | x
| x |  |  |  |  | M2
W12 | x
TUE 5.12 | x
| x | [7 empty] | M3
W13
TUE 12.12
W14
TUE 19.12
DEADLINE FRI 22.12 | [11 empty] | (M4)
M5